## Project Plan and Timing
Sertan |  | Burak | [10 empty] | Analiz Girdi
Mustafa |  | Kıvanç | [10 empty] | Ön çalışma
Taşkın |  | ERER | [10 empty] | Ref. çalışma
Coşkun |  | TEMPA | [10 empty] | Planlanan
|  | Outsource | [10 empty] | Tamamlanan
[13 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028
| Number |  | Name | Type | Ekip | Sorumlu | Status |  |  | PROJE | CAE Resp. | CAD Data Readiness | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC
[7 empty] | Phase 2 | Phase3 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
|  | PROJECT TIMING | [10 empty] | JAN 1: G3; FEB 6: G3.1; MARCH 10: G3.2
| 6 | CFD | Exterior Aerodynamic (NGC) | CFD | End. Tasarım |  | - | On going | #REF! | NGC Maraton | Kıvanç | bar: JAN 1 to DEC 52
| 19 | CFD | Air Channel (HVAC) | CFD | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | NGC Maraton | Taşkın | bar: JAN 1 to DEC 52
| 20 | CFD | Soil Analysis | CFD | End. Tasarım/Gövde | Görkem Bulkan | - | Planning | #REF! | NGC Maraton | Kıvanç | bar: JAN 1 to DEC 52
| 21 | CFD | Defroster Hava Kanalı | CFD | Hvac/Trim | Efe Çukur | - | Planning | #REF! | NGC Maraton | Taşkın | bar: JAN 1 to DEC 52
|  |  | FEM Modelling | [6 empty] | NGC Maraton | Coşkun | bar: JAN 1 to DEC 52
| 1 | Safety | Rollover (EU) (ECE R66.02) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | OK | Planning | #REF! | NGC Maraton | Coşkun |  | JAN 1: 3; FEB 6: 1; MARCH 13: 1; APRIL 15: 1; APRIL 18: 1
| 8 | Safety | Frontal Crash / FUPD (ECE R29/R93) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC Maraton | Coşkun | bar: JAN 1 to DEC 52
| 2 | Durability | Body/Chassis/Statik | Body Static Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | Critically Ok | Planning | #REF! | NGC Maraton | Mustafa | bar: JAN 1 to DEC 52
| 7 | Durability | Body/Chassis Fatigue | Fatigue | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC Maraton | Sertan | bar: JAN 1 to DEC 52
|  | Durability | Kayar Basamak Analizi | Modal/Static | [5 empty] | NGC Maraton | TEMPA | bar: JAN 1 to DEC 52
| 34 | Durability | Arka Çeki Analizi | Fatigue | Gövde | Mustafa Tokat | - | Planning | #REF! | NGC Maraton | Mustafa | bar: JAN 1 to DEC 52
| 10 | Durability | Wiper Motor and Mechanism | Modal/Static | Gövde | Süleyman Ezer | - | Planning | #REF! | NGC Maraton | Burak | Hazır | bar: JAN 1 to DEC 52
| 14 | Durability | Steering Column Assembly | Crashworthiness | Mekanik | Tarık Alkaya | - | Planning | #REF! | NGC Maraton | Mustafa | bar: JAN 1 to DEC 52
| 15 | Durability | Front Defroster Brackets | Modal/Static | Hvac | Mehmet Sakallı | - | Planning | #REF! | NGC Maraton | Burak | Hazırlanacak | bar: JAN 1 to DEC 52
| 16 | Durability | Destination Panel Brackets | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı | bar: JAN 1 to DEC 52
| 17 | Durability | Monitor Brackets | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı | bar: JAN 1 to DEC 52
| 18 | Durability | Exterior Mirror Assembly | Modal/Static | Trim | Mehmet Oflazoğlu | - | Planning | #REF! | NGC Maraton | Burak | Hazır | bar: JAN 1 to DEC 52
| 22 | Durability | Modesty Panel | Modal/Static | Trim | ramazan Kaplan | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı | bar: JAN 1 to DEC 52
| 23 | Durability | Rear Headlining | Modal/Static | Trim | Vural Kart | - | Planning | #REF! | NGC Maraton | TEMPA | bar: JAN 1 to DEC 52
| 24 | Durability | Front Headlining | Modal/Static | Trim | Oğuz Sürer | - | Planning | #REF! | NGC Maraton | TEMPA | bar: JAN 1 to DEC 52
| 25 | Durability | Dashboard | Modal/Static | Trim | Efe Çukur | - | Planning | #REF! | NGC Maraton | Sertan | bar: JAN 1 to DEC 52
| 27 | Durability | Block Headlamp | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | W15 | bar: JAN 1 to DEC 52
| 29 | Durability | Refrigerator Bracket | Modal/Static | Trim | Emirhan Koç | - | Planning | #REF! | NGC Maraton | Burak | bar: JAN 1 to DEC 52
| 30 | Durability | WC Bracket | Modal/Static | Trim | ? | - | Planning | #REF! | NGC Maraton | Burak | bar: JAN 1 to DEC 52
|  | Durability | Organizer Component Analizi | Static | Hvac | Mehmet Sakallı |  |  |  | NGC Maraton | Burak | Hazırlanacak | bar: JAN 1 to DEC 52
| 31 | Durability | Compressor Bracket | Modal/Static | Mekanik | Tarık Alkaya | - | Planning | #REF! | NGC Maraton | Burak | bar: JAN 1 to DEC 52
| 11 | Durability | Luggage Lids/Hinge Connections | Static | Gövde | Serkan Yeğenoğlu | - | Planning | #REF! | NGC Maraton | Burak | Hazır. Atılmadı | bar: JAN 1 to DEC 52
| 28 | Durability | Critical Seat Location | Static | Trim/Gövde | Emirhan Koç | - | Planning | #REF! | NGC Maraton | Coşkun | bar: JAN 1 to DEC 52
| 35 | Durability | Ön Çeki Analizi | Static | Gövde | Saim Kaltar | - | Planning | w6 | NGC Maraton | Mustafa | bar: JAN 1 to DEC 52
| 36 | Durability | Luggage Thickness | Static | Gövde | Süleyman Ezer | - | Ongoing | #REF! | NGC Maraton | Coşkun | Hazır | bar: JAN 1 to DEC 52
| 32 | Durability | Yan spoiler braketi | Static (Aero yükleriyle) | Gövde | Saim kaltar | - | Planning | #REF! | NGC Maraton | Burak | CAE Ekibi | bar: JAN 1 to DEC 52
| 33 | Durability | Fender Braketi | Static (Aero yükleriyle) | Gövde | Süleyman Ezer | - | Planning | #REF! | NGC Maraton | Burak | CAE Ekibi | bar: JAN 1 to DEC 52
| 9 | NVH | Body Torsional Stiffness Analysis | Body Torsional Stiffness Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC Maraton | Mustafa | bar: JAN 1 to DEC 52
| 5 | NVH | Body Modal Analysis | Modal | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | On going | Planning | #REF! | NGC Maraton | Sertan | bar: JAN 1 to DEC 52
|  | VS | VS0 Reporting | [5 empty] | #REF! | NGC Maraton | Report | bar: JAN 1 to DEC 52
|  |  | VS1 Reporting | [6 empty] | NGC Maraton | Report |  | MAY 19: 6; JUNE 23: 6
|  | Analysis | ALL | [5 empty] | #REF! | NGC Maraton | ALL |  | JAN 1: 3; FEB 6: 3.5; MARCH 10: 4; APRIL 15: 5.75; MAY 19: 6.8; JUNE 23: 2.8; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[13 empty] | G3.2 | [26 empty] | G4-5
| 19 | Durability | FEM Modelling |  | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | Aveneu Neo | Sertan | bar: FEB 8 to MARCH 11
| 21 | Durability | Body/Chassis Static | Body Static Analysis | Hvac/Trim | Efe Çukur | - | Planning | #REF! | Aveneu Neo | Sertan | bar: FEB 6; MARCH 13; APRIL 15
|  | Durability | Body/Chassis Fatigue | Fatigue | [5 empty] | Aveneu Neo | Sertan | bar: AUG 32 to SEP 37
|  | Durability | Component Analysis | Modal/Static | [5 empty] | Aveneu Neo | Burak | Component Sayfasında Detay Mevcut | bar: FEB 9 to MAY 20
|  | NVH | Body Torsional Stiffness Analysis | Stiffness | [5 empty] | Aveneu Neo | Sertan | bar: JUNE 25 to JUNE 26
| 1 | Safety | Rollover (EU) (ECE R66.02) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | OK | Planning | #REF! | Aveneu Neo | Sertan | bar: FEB 7; MARCH 12; MARCH 14; APRIL 16 to APRIL 17
| 8 | Safety | Frontal Crash / FUPD (ECE R29/R93) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | Aveneu Neo | ERER | bar: JAN 1 to JAN 2
|  | Safety | Rear Crash / RUPD (ECE R58) | Crashworthiness | [5 empty] | Aveneu Neo | Coşkun | bar: APRIL 15 to MAY 20
| 9 | CFD | Defroster Hava Kanalı | CFD | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | Aveneu Neo | Taşkın | bar: FEB 8 to MARCH 11
| 5 | CFD | Air Channel (HVAC) | CFD | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | On going | Planning | #REF! | Aveneu Neo | Taşkın | bar: MARCH 12 to MAY 21
|  | CFD | Soil Analysis | CFD | [5 empty] | Aveneu Neo | - | bar: MARCH 14 to MAY 19; JUNE 23 to JULY 28
|  | VS | VS0 Reporting | [5 empty] | #REF! | Aveneu Neo | Report | bar: APRIL 15 to APRIL 18
|  |  | VS1 Reporting | [6 empty] | Aveneu Neo | Report | bar: JUNE 25 to JUNE 27
|  | Analysis | ALL | [5 empty] | #REF! | Aveneu Neo | ALL |  | JAN 1: 0.4; FEB 6: 1.75; MARCH 10: 3.2; APRIL 15: 3.75; MAY 19: 1.75; JUNE 23: 1; JULY 28: 0; AUG 32: 1; SEP 37: 0.25; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
| 19 |  | FEM Modelling |  | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | 12m Upgrade | ERER | bar: FEB 8 to MARCH 11
| 19 | Safety | R66.02 | Crashworthiness | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | 12m Upgrade | ERER | bar: MARCH 12 to APRIL 15
| 21 | Durability | Body/Chassis Static | Body Static Analysis | Hvac/Trim | Efe Çukur | - | Planning | #REF! | 12m Upgrade | bar: MARCH 12 to MARCH 13
|  | Analysis | ALL | [5 empty] | #REF! | 12m Upgrade | ALL |  | JAN 1: 0; FEB 6: 0.5; MARCH 10: 1.4; APRIL 15: 0.25; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[13 empty] | G3 | [51 empty] | G3 | [51 empty] | G3
| 19 |  | FEM Modelling |  | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | MD9 LHD WCL | Mustafa | bar: FEB 6 to FEB 9
| 19 | Safety | R66.02 | Crashworthiness | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | MD9 LHD WCL | Mustafa | bar: MARCH 10 to MARCH 13
| 21 | Durability | Body/Chassis Static | Body Static Analysis | Hvac/Trim | Efe Çukur | - | Planning | #REF! | MD9 LHD WCL | Mustafa | bar: MARCH 14 to APRIL 15
|  | Analysis | ALL | [5 empty] | #REF! | MD9 LHD WCL | ALL |  | JAN 1: 0; FEB 6: 1; MARCH 10: 1; APRIL 15: 0.25; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[13 empty] | G3.1 | [8 empty] | G3.2 | [26 empty] | G4-5
| 19 | Durability | Engine Mount Bracket | Modal/Static | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS45 X10 | Mustafa | bar: JAN 1 to JAN 5
| 19 | Durability | Chassis Durability | Body Static Analysis | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS45 X10 | Mustafa | bar: JAN 1 to JAN 2
| 21 | Safety | FMVSS 227 | Crashworthiness | Hvac/Trim | Efe Çukur | - | Planning | #REF! | TS45 X10 | Coşkun |  | FEB 6: 3
|  | Analysis | ALL | [5 empty] | #REF! | TS45 X10 | ALL |  | JAN 1: 1.4; FEB 6: 0.75; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[13 empty] | G3.1 | [8 empty] | G3.2 | [39 empty] | G4-5
| 19 | Durability | Engine Mount Bracket | Modal/Static | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS35 X10 | Mustafa | bar: APRIL 15 to APRIL 17; MAY 19 to MAY 20; MAY 22 to JUNE 23
| 19 | Durability | Chassis Durability | Body Static Analysis | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS35 X10 | Mustafa | bar: APRIL 18; MAY 21; JUNE 24
| 21 | Safety | FMVSS 227 | Crashworthiness | Hvac/Trim | Efe Çukur | - | Planning | #REF! | TS35 X10 | Coşkun |  | JUNE 23: 3
|  | Analysis | ALL | [5 empty] | #REF! | TS35 X10 | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 1; MAY 19: 1; JUNE 23: 1; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | OCT |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[31 empty] | G3.1 | [17 empty] | G3.2
| 19 | Durability | Engine Mount Bracket | Modal/Static | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS30 X10 | Mustafa | bar: JULY 28 to JULY 30; AUG 32 to AUG 33; AUG 35 to AUG 36
| 19 | Durability | Chassis Durability | Body Static Analysis | Hvac/Trim | Halit Çalışkan | - | Planning | #REF! | TS30 X10 | Mustafa | bar: JULY 31; AUG 34; SEP 37
| 21 | Safety | FMVSS 227 | Crashworthiness | Hvac/Trim | Efe Çukur | - | Planning | #REF! | TS30 X10 | Coşkun |  | SEP 39: 1; OCT 41: 2
|  | Analysis | ALL | [5 empty] | #REF! | TS30 X10 | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 1; AUG 32: 1; SEP 37: 0.5; OCT 41: 0.5; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; OCT 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
G3
|  |  | FEM Modelling |  | End. Tasarım/Gövde | Görkem Bulkan | - | Planning | #REF! | CITY ONE | - | bar: MAY 21 to JULY 28; FEB 6 to FEB 8; MARCH 11 to MARCH 13
|  | Durability | Chassis Durability | Body Static Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | OK | Planning | #REF! | CITY ONE | - | bar: JUNE 27 to AUG 34; JAN 2 to JAN 3; FEB 5 to FEB 6; MARCH 12 to MAY 19
|  | Durability | Fatigue | Fatigue | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | CITY ONE | - | bar: SEP 40 to NOV 45; NOV 47 to DEC 52; JAN 3 to JAN 4; FEB 7 to FEB 8; JUNE 25 to JUNE 26; JULY 29 to JULY 30; AUG 32 to AUG 33; SEP 36 to SEP 37
|  | Durability | Component Gövde | Modal/Static | Trim | Emirhan Koç | - | Planning | #REF! | CITY ONE | - | bar: AUG 32 to AUG 36; SEP 38 to SEP 40; OCT 42 to NOV 45; JAN 3 to JAN 4; FEB 7 to FEB 8; APRIL 17 to MAY 18; JUNE 23; JUNE 25; JULY 27; JULY 30
|  | Durability | Component Mekanik | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | Critically Ok | Planning | #REF! | CITY ONE | - | bar: AUG 35 to AUG 36; SEP 39 to NOV 45; JAN 3 to JAN 4; MAY 20 to MAY 21; JUNE 24 to JUNE 25; JULY 28; JULY 30
|  | Durability | Component Trim | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | CITY ONE | - | bar: JULY 28 to DEC 51; JAN 3 to JAN 4; MARCH 13 to APRIL 14; APRIL 17; MAY 22 to JUNE 23; JUNE 26; JULY 28 to JULY 29; AUG 31 to AUG 32; AUG 35 to SEP 36
|  | NVH | Torsional Stiffness | Stiffness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | Critically Ok | Planning | #REF! | CITY ONE | - | bar: JUNE 25 to JUNE 26; NOV 45 to NOV 46; DEC 51 to JAN 2; MARCH 10 to MARCH 11; AUG 33 to AUG 34; SEP 36 to SEP 37
|  | NVH | Body Modal | Modal | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | CITY ONE | - | bar: JUNE 27 to JULY 28; JULY 31 to AUG 34; OCT 41 to OCT 42; NOV 45; DEC 50 to DEC 51; MARCH 12 to MARCH 13; APRIL 15 to APRIL 17; MAY 19; JUNE 26 to JULY 27; JULY 30
|  | SAFETY | R66.02 | Crashworthiness | Gövde |  | Done | - | #REF! | CITY ONE | - | bar: JUNE 25 to JUNE 26; JULY 29 to JULY 30; AUG 35 to SEP 38; JAN 3 to JAN 4; FEB 7 to FEB 8; MARCH 10 to MARCH 11; APRIL 14 to APRIL 15; MAY 20 to JUNE 23
|  | SAFETY | R29 & 93 | Crashworthiness | Gövde | Serkan Yeğenoğlu | - | Planning | #REF! | CITY ONE | - | bar: JULY 28 to JULY 31; AUG 35 to AUG 36; SEP 39 to SEP 40; MARCH 13 to APRIL 14; MAY 18 to MAY 19; JUNE 24 to JUNE 25
|  | CFD | Aerodynamics (Soil,Wading,Multi-Phase,etc.) | CFD | [5 empty] | CITY ONE | Kıvanç | bar: APRIL 15 to JUNE 27; SEP 37 to SEP 39; NOV 45 to NOV 48; DEC 51 to MARCH 12; MAY 22 to JUNE 24
|  | CFD | Thermal Comfort | CFD | [5 empty] | CITY ONE | Taşkın | bar: JUNE 23 to JULY 31; AUG 34 to SEP 38; JAN 2 to FEB 6; FEB 8 to MARCH 9; MARCH 12 to APRIL 16; MAY 19 to JUNE 23
|  | CFD | Thermal CAE | CFD | [5 empty] | CITY ONE | Kıvanç | bar: MAY 19 to MAY 22; OCT 43 to DEC 50; JAN 0 to JAN 2; FEB 5 to FEB 7; MAY 19 to MAY 20; JULY 28 to AUG 35
|  | VS | VS0 Reporting | [6 empty] | CITY ONE | Team | bar: JULY 30 to AUG 33; SEP 38 to OCT 41; MAY 18 to MAY 19; JUNE 25 to JULY 28
|  |  | VS1 Reporting | [6 empty] | CITY ONE | Team | bar: NOV 45 to DEC 52; AUG 32 to SEP 39
|  | Analysis | 4 Araç (18m,12m) | [5 empty] | #REF! | CITY ONE | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 1; MAY 19: 2.5; JUNE 23: 4.2; JULY 28: 5.75; AUG 32: 5.4; SEP 37: 5.5; OCT 41: 5; NOV 45: 4.6; DEC 50: 4; JAN 0: 5.2; FEB 5: 5.25; MARCH 9: 4; APRIL 14: 4; MAY 18: 4.25; JUNE 23: 4.25; JULY 27: 3.75; AUG 31: 3.2; SEP 36: 1.25; OCT 40: 0; NOV 44: 0; DEC 49: 0; JAN 0: 0; FEB 5: 0; MARCH 9: 0; APRIL 14: 0; MAY 18: 0; MAY 22: 0; JULY 27: 0; AUG 31: 0; SEP 36: 0; OCT 40: 0; NOV 44: 0; DEC 49: 0
SUM 65 18 ay
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 0: 2027; JAN 0: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
G3 & G3.1
|  | CFD | Exterior Aerodynamic (NGC) | CFD | End. Tasarım |  | - | On going | #REF! | NGC HD | - | bar: JUNE 23 to JUNE 27; SEP 39 to SEP 40; NOV 45 to NOV 46; DEC 50; DEC 52 to JAN 1; FEB 5 to FEB 6
|  | CFD | Soil Analysis | CFD | End. Tasarım/Gövde | Görkem Bulkan | - | Planning | #REF! | NGC HD | - | bar: JULY 28 to JULY 31
|  | CFD | Thermal CAE | CFD | [5 empty] | NGC HD | bar: JAN 2 to JAN 3; FEB 7 to FEB 8
|  | CFD | Termal Comfort | CFD | [5 empty] | NGC HD | bar: OCT 42 to OCT 43; DEC 50 to DEC 51; JAN 2 to JAN 3
|  |  | FEM Modelling |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | OK | Planning | #REF! | NGC HD | - | bar: JULY 28 to JULY 31
|  | Durability | Chassis Durability | Body Static Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC HD | - | bar: AUG 32 to AUG 33
|  | Durability | Fatigue | Fatigue | [5 empty] | NGC HD | - | bar: AUG 34 to SEP 37
|  | Durability | Component Gövde | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | Critically Ok | Planning | #REF! | NGC HD | - | bar: OCT 41 to OCT 42; DEC 50; JAN 0
|  | Durability | Component Mekanik | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC HD | - | bar: NOV 48 to NOV 49; DEC 51; JAN 0
|  | Durability | Component Trim | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC HD | - | bar: OCT 41 to OCT 42; NOV 45 to NOV 46; DEC 50; JAN 1 to JAN 2; FEB 5
|  | Safety | R66.02 | Crashworthiness | [5 empty] | NGC HD | - | bar: AUG 36 to SEP 37; SEP 40 to OCT 42; NOV 45 to NOV 47
|  | Safety | R29 & 93 | Crashworthiness | [5 empty] | NGC HD | - | bar: AUG 34 to AUG 35; SEP 38 to SEP 39; OCT 43 to OCT 44
|  | NVH | Body Torsional Stiffness Analysis | Body Torsional Stiffness Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC HD | - | bar: SEP 37 to SEP 38
|  | NVH | Body Modal Analysis | Modal | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | On going | Planning | #REF! | NGC HD | - | bar: AUG 35 to SEP 38; DEC 51 to DEC 52
|  | VS | VS0 Reporting | [6 empty] | NGC HD | Team | bar: SEP 39 to OCT 42; JAN 2 to JAN 3
|  |  | VS1 Reporting | [6 empty] | NGC HD | Team | bar: NOV 45 to NOV 49; FEB 5 to FEB 6
|  | Analysis | ALL | [5 empty] | #REF! | NGC HD | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 1; JULY 28: 2; AUG 32: 2; SEP 37: 3.25; OCT 41: 3; NOV 45: 2.8; DEC 50: 3; JAN 0: 2.4; FEB 5: 1.75; MARCH 9: 0; APRIL 14: 0; MAY 18: 0; MAY 22: 0; JULY 27: 0; AUG 31: 0; SEP 36: 0; OCT 40: 0; NOV 44: 0; DEC 49: 0; JAN 0: 0; FEB 5: 0; MARCH 9: 0; APRIL 14: 0; MAY 18: 0; MAY 22: 0; JULY 27: 0; AUG 31: 0; SEP 36: 0; OCT 40: 0; NOV 44: 0; DEC 49: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 0: 2027; JAN 0: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[13 empty] | G3.2 | [26 empty] | G4-5 | [24 empty] | G3.2 | [26 empty] | G4-5 | [24 empty] | G3.2 | [26 empty] | G4-5
|  |  | FEM Modelling |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC HD RHD | - | bar: OCT 43 to OCT 44
|  | Safety | Frontal Crash / FUPD (ECE R29/R93) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC HD RHD | - | bar: NOV 45 to NOV 46; NOV 48 to NOV 49
|  | Analysis | ALL | [5 empty] | #REF! | NGC HD RHD | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0.5; NOV 45: 0.4; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
[79 empty] | G3 | [12 empty] | G3.1 | [12 empty] | G3.2
|  | CFD | Exterior Flow (Aero,Wading,Multiphase,Soil) | CFD | End. Tasarım |  | - | On going | #REF! | NGC RD | - | bar: MARCH 9 to MARCH 10; MARCH 12 to AUG 31
|  | CFD | Thermal CAE | CFD | [5 empty] | NGC RD | bar: MARCH 11 to MARCH 12; APRIL 14 to APRIL 17; MAY 22 to JUNE 26
|  | CFD | Thermal Comfort | CFD | End. Tasarım/Gövde | Görkem Bulkan | - | Planning | #REF! | NGC RD | - | bar: MAY 18 to MAY 21; JULY 27 to AUG 31
|  |  | FEM Modelling |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | OK | Planning | #REF! | NGC RD | - | bar: JULY 27 to AUG 32
|  | Durability | Chassis Durability | Crash | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC RD | - | bar: MARCH 12 to MARCH 13; AUG 33 to AUG 34
|  | Durability | Fatigue | Fatigue | [5 empty] | NGC RD | - | bar: MAY 20 to MAY 21; JUNE 25 to JUNE 26; AUG 35 to SEP 38
|  | Durability | Component Gövde | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | Critically Ok | Planning | #REF! | NGC RD | - | bar: OCT 40 to OCT 41; NOV 44 to NOV 45; NOV 47 to DEC 50
|  | Durability | Component Mekanik | Modal/Static | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC RD | - | bar: OCT 40 to OCT 41; NOV 45 to NOV 46
|  | Durability | Component Trim | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC RD | - | bar: AUG 33 to AUG 34; OCT 40 to NOV 44; NOV 47 to DEC 51
|  | Safety | R66.02 | Crashworthiness | [5 empty] | NGC RD | - | bar: AUG 35 to SEP 36; SEP 39 to OCT 41; NOV 44 to NOV 46
|  | Safety | R29 & 93 | Crashworthiness | [5 empty] | NGC RD | - | bar: MARCH 10 to MARCH 11; AUG 33 to AUG 34; SEP 37 to SEP 38; OCT 42 to OCT 43
|  | NVH | Body Torsional Stiffness Analysis | Body Torsional Stiffness Analysis | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC RD | - | bar: SEP 36 to SEP 37
|  | NVH | Body Modal Analysis | Modal | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | On going | Planning | #REF! | NGC RD | - | bar: AUG 34 to SEP 37
|  | VS | VS0 Reporting | [6 empty] | NGC RD | Team | bar: SEP 38 to OCT 40; OCT 43 to NOV 45
|  |  | VS1 Reporting | [6 empty] | NGC RD | Team |  | NOV 47: 1; NOV 48: 1; DEC 49: 4
|  | Analysis | ALL | [5 empty] | #REF! | NGC RD | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 0: 0; FEB 5: 0; MARCH 9: 2; APRIL 14: 2; MAY 18: 2.5; MAY 22: 2.4; JULY 27: 3; AUG 31: 2.8; SEP 36: 3.25; OCT 40: 3.5; NOV 44: 3.2; DEC 49: 3; JAN 0: 0; FEB 5: 0; MARCH 9: 0; APRIL 14: 0; MAY 18: 0; MAY 22: 0; JULY 27: 0; AUG 31: 0; SEP 36: 0; OCT 40: 0; NOV 44: 0; DEC 49: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 0: 2027; JAN 0: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
|  |  | FEM Modelling |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC RD RHD | - | bar: OCT 43 to OCT 44
|  | Safety | Frontal Crash / FUPD (ECE R29/R93) | Crashworthiness | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | NGC RD RHD | - | bar: NOV 45 to NOV 46; NOV 48 to NOV 49
|  | Analysis | ALL | [5 empty] | #REF! | NGC RD RHD | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0.5; NOV 45: 0.4; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[40 empty] | G3 | [76 empty] | G3.2
|  |  | FEM Modelling |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | EURO 7 | - | bar: JULY 28 to AUG 36; OCT 43 to NOV 48; FEB 6 to MARCH 14; JUNE 23 to JUNE 27
|  | Durability | Component | Modal/Static | [5 empty] | EURO 7 | - | bar: OCT 43 to OCT 44; DEC 50 to JAN 5; JULY 28 to AUG 36
|  | Safety | Rollover (EU) (ECE R66.02) | Crashworthiness | [5 empty] | EURO 7 | - | bar: SEP 37 to OCT 44; APRIL 15 to MAY 22; SEP 37 to OCT 44
|  | Analysis | 7 Araç | [5 empty] | #REF! | EURO 7 | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 1; AUG 32: 1; SEP 37: 1; OCT 41: 1; NOV 45: 1; DEC 50: 1; JAN 1: 1; FEB 6: 1; MARCH 10: 1; APRIL 15: 1; MAY 19: 1; JUNE 23: 1; JULY 28: 1; AUG 32: 1; SEP 37: 1; OCT 41: 1; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
|  |  | FEM Modelling (27kW) |  | Gövde | Kasım Poyraz/Saim Kaltar/Mustafa Tokat | - | Planning | #REF! | A1327 LFP Batarya | - | bar: MAY 21 to JUNE 24
|  | Safety | R100 - Mechanical Shock(27kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: JUNE 25 to JULY 28
|  | Safety | R100 - Drop Test (27kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: JULY 29 to AUG 32
|  | Safety | R100 - Side Impact (27kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: AUG 33 to AUG 36
|  |  | FEM Modelling (99kW) | [6 empty] | A1327 LFP Batarya | - | bar: JUNE 25 to JULY 28
|  | Safety | R100 - Mechanical Shock(99kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: JULY 29 to AUG 32
|  | Safety | R100 - Drop Test (99kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: AUG 33 to AUG 36
|  | Safety | R100 - Side Impact (99kW) | Crashworthiness | [5 empty] | A1327 LFP Batarya | - | bar: SEP 37 to SEP 40
|  | CFD | Battery Thermal CAE (27kW) | CFD | [5 empty] | A1327 LFP Batarya | - | bar: MAY 19 to MAY 22; JUNE 27 to JULY 30; AUG 35 to SEP 37; OCT 41 to OCT 42
|  | CFD | Battery Thermal CAE (99kW) | CFD | [5 empty] | A1327 LFP Batarya | - | bar: JUNE 23 to JUNE 26; JULY 31 to AUG 34; SEP 38 to OCT 44
|  | Analysis | A1327 LFP | [5 empty] | #REF! | A1327 LFP | ALL |  | JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 1.5; JUNE 23: 2.6; JULY 28: 3; AUG 32: 3; SEP 37: 2; OCT 41: 1.5; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0; JAN 1: 0; FEB 6: 0; MARCH 10: 0; APRIL 15: 0; MAY 19: 0; JUNE 23: 0; JULY 28: 0; AUG 32: 0; SEP 37: 0; OCT 41: 0; NOV 45: 0; DEC 50: 0
|  | PROJECT TIMING | [10 empty] | JAN 1: 2026; JAN 1: 2027; JAN 1: 2028
[13 empty] | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  | JAN |  |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
|  | Analysis | [6 empty] | #REF! | MEVCUT CITY | ALL |  | JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1
|  | Analysis | [7 empty] | MEVCUT INTERCITY | ALL |  | JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1
|  | Analysis | [7 empty] | MEVCUT EU COACH | ALL |  | JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1
|  | Analysis | [7 empty] | MEVCUT NA COACH | ALL |  | JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1
|  | Analysis | [7 empty] | MEVCUT MIDIBUS | ALL |  | JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1; JAN 1: 0.1; FEB 6: 0.1; MARCH 10: 0.1; APRIL 15: 0.1; MAY 19: 0.1; JUNE 23: 0.1; JULY 28: 0.1; AUG 32: 0.1; SEP 37: 0.1; OCT 41: 0.1; NOV 45: 0.1; DEC 50: 0.1
Note on D26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: data hazır. göndermediler.
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ramazan Kaplan: Daha tasarıma başlanmadı.
Note on D34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: braket çalışacaklar. data henüz gönderilmedi.
Note on D36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data gönderecekler

## Component
[10 empty] | CAD Data | Gerekli İnputlar ve loadcase | DVP | FE Model | Analiz | İterasyon | Raporlama
| Name | Type | Ekip | Sorumlu | Status |  | Status |  | CAE Resp.
Durability | Wiper Motor and Mechanism | Modal/Static | Gövde | Süleyman Ezer | - | Planning | #REF! | NGC Maraton | Burak | Hazır | İnput ve loadcaseler toplanacak.
Durability | Front Defroster Brackets | Modal/Static | Hvac | Mehmet Sakallı | - | Planning | #REF! | NGC Maraton | Burak | R29 sonucu bekleniyor
Durability | Destination Panel Brackets | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı
Durability | Monitor Brackets | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı. Net tarih yok.
Durability | Exterior Mirror Assembly | Modal/Static | Trim | Mehmet Oflazoğlu | - | Planning | #REF! | NGC Maraton | Burak | Hazır | İnput ve loadcaseler toplandı. |  | Hazırlanıyor
Durability | Modesty Panel | Modal/Static | Trim | Ramazan Kaplan | - | Planning | #REF! | NGC Maraton | Burak | Başlanmadı
Durability | Block Headlamp | Modal/Static | Trim | Mustafa Topal | - | Planning | #REF! | NGC Maraton | Burak | W16 da iletilecek
Durability | Refrigerator Bracket | Modal/Static | Trim | Emirhan Koç | - | Planning | #REF! | NGC Maraton | Burak | Nihai data hazır değil | [6 empty] | Planning | Work in Progress | Completed
Durability | WC Bracket | Modal/Static | Trim | ? | - | Planning | #REF! | NGC Maraton | Burak | Henüz hazır değil
Durability | Organizer Component | Static | Hvac | Mehmet Sakallı |  |  |  | NGC Maraton | Burak | Braket tasarımı çalışılıyor. | [6 empty] | Durability | Rear Towing Hook Assy | Static | Gövde
Durability | Compressor Bracket | Modal/Static | Mekanik | Tarık Alkaya | - | Planning | #REF! | NGC Maraton | Burak | Henüz bakılmadı | [6 empty] | Durability | Front Towing Hook Assy | Static | Gövde
Durability | Luggage Lids/Hinge Connections | Static | Gövde | Serkan Yeğenoğlu | - | Planning | #REF! | NGC Maraton | Burak | Data gelmedi | [6 empty] | Durability | Optional Rear Towing Hook Assy | Static | Gövde
Durability | Yan spoiler braketi | Static (Aero yükleriyle) | Gövde | Saim kaltar | - | Planning | #REF! | NGC Maraton | Burak | CAE Ekibi ile yürütülecek | [6 empty] | Durability | Plate Windshield Wiper Motor | Static/Modal | Gövde
Durability | Fender Braketi | Static (Aero yükleriyle) | Gövde | Süleyman Ezer | - | Planning | #REF! | NGC Maraton | Burak | CAE Ekibi ile yürütülecek | [6 empty] | Safety | Rear Underrun Protection Device | ECE R-58 | Gövde
Durability | Rear Towing Hook Assy | Static | Gövde | Süleyman Kuş/Erkan Kırgıl | - | Planning | #REF! | Aveneu Neo | Burak | Hazır | Hazır. (Mail ile atıldı. DVP olarak atılmadı) | Yok |  |  |  |  | Durability | Bevel Box Bracket | Static/Modal | Mekanik
Durability | Front Towing Hook Assy | Static | Gövde | Süleyman Kuş/Erkan Kırgıl |  |  |  | Aveneu Neo | Burak | Hazır | Hazır. (Mail ile atıldı. DVP olarak atılmadı) | Yok |  |  |  |  | Durability | Steering Box | Static/Modal | Mekanik
Safety | Battery Bracket | R-100 | Elektrik | Furkan Taşlı |  |  |  | Aveneu Neo | Coşkun | Hazır | Hazır (ECE R-100) | Regülasyon |  |  |  |  | Durability | Steering Hydraulic Motor | Static/Modal | Mekanik
Durability | Plate Windshield Wiper Motor | Static/Modal | Gövde | Süleyman Kuş/Erkan Kırgıl |  |  |  | Aveneu Neo | Burak | Hazır | Input ve loadcaseler toplandı. | Yok |  |  |  |  | Safety | Battery Carcass | R-100 | Elektrik
Durability | Bevel Box Bracket | Static/Modal | Mekanik | Alican Ak |  |  |  | Aveneu Neo | Burak | Hazır | Input ve loadcaseler ekipler arası belirlenecek. | Yok |  |  |  |  | Safety | Battery Bracket | R-100 | Elektrik
Durability | Optional Rear Towing Hook Assy | Static | Gövde | Süleyman Kuş/Erkan Kırgıl |  |  |  | Aveneu Neo | Burak | Hazır | Hazır. (Mail ile atıldı. DVP olarak atılmadı) | Yok |  |  |  |  | CFD | Defogging | SAE J381 | HVAC/Trim
Safety | Battery Carcass | R-100 | Elektrik | Furkan Taşlı |  |  |  | Aveneu Neo | Coşkun | Hazır | Hazır (ECE R-100) | Regülasyon
Durability | Steering Box | Static/Modal | Mekanik | Alican Ak | A |  |  | Aveneu Neo | Burak | Hazır | Input ve loadcaseler ekipler arası belirlenecek. | Yok
Durability | Steering Hydraulic Motor | Static/Modal | Mekanik | Alican Ak | A |  |  | Aveneu Neo | Sertan | Hazır | Input ve loadcaseler toplandı. | Yok | Hazır | Yapıldı | İlk iterasyonda sonuç OK | Raporlandı
Safety | Rear Underrun Protection Device | ECE R-58 | Gövde | Süleyman Kuş/Erkan Kırgıl |  |  |  | Aveneu Neo | Coşkun | Hazır | Hazır ( ECE R-58) | Regülasyon
Durability | Skibox Perno | Static | Gövde | Murat Demirdüzen |  |  |  | Prestij | Burak | Hazır | Input ve loadcaseler toplandı. |  | Hazır | Yapıldı | İlk iterasyonda sonuç OK | Raporlandı
Note on K5: Burak Şahin: R29 sonucu bekleniyor
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: data hazır. göndermediler.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ramazan Kaplan: Daha tasarıma başlanmadı.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: braket çalışacaklar. data henüz gönderilmedi.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data gönderecekler

## Sheet2
[5 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[5 empty] | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEP | OCT | OCT | DEC
| Analysis | ALL | NGC Maraton | ALL | 3 | 4.5 | 4.6 | 6.25 | 5.6 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | Aveneu Neo | ALL | 1.4 | 1.75 | 3.2 | 3.75 | 1.75 | 1 | 0 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | 12m Upgrade | ALL | 0 | 0.5 | 1.4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | MD9 LHD WCL | ALL | 0 | 1 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | TS45 X10 | ALL | 1.4 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | TS35 X10 | ALL | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | TS30 X10 | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sum 65 18 ay | Analysis | 4 Araç (18m,12m) | CITY ONE | ALL | 0 | 0 | 0 | 1 | 2.5 | 4.2 | 5.75 | 5.4 | 5.5 | 5 | 4.6 | 4 | 5.2 | 5.25 | 4 | 4 | 4.25 | 4.25 | 3.75 | 3.2 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | NGC HD | ALL | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3.25 | 3 | 2.8 | 3 | 2.4 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | NGC HD RHD | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | NGC RD | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2.5 | 2.4 | 3 | 2.8 | 3.25 | 3.5 | 3.2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | ALL | NGC RD RHD | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis | 7 Araç | EURO 7 | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Analysis | A1327 LFP | A1327 LFP | ALL | 0 | 0 | 0 | 0 | 1.5 | 2.6 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis |  | MEVCUT CITY | ALL | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Analysis |  | MEVCUT INTERCITY | ALL | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Analysis |  | MEVCUT EU COACH | ALL | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Analysis |  | MEVCUT NA COACH | ALL | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Analysis |  | MEVCUT MIDIBUS | ALL | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| SUM |  |  |  | 6.8 | 9 | 10.7 | 13 | 12.85 | 12.5 | 12.25 | 12.9 | 12 | 9.5 | 8.3 | 7.5 | 8.1 | 7.5 | 6.5 | 6.5 | 7.25 | 7.15 | 8.25 | 7.5 | 6 | 5.5 | 5.1 | 4.5 | 3.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0